## Resource work activity chart
RESOURCE WORK ACTIVITY CHART
Activities |  | Duration | Start | End | Resource
1. Licensing & Venue |  | 8 days | 2022-03-01 | 2022-03-08 | Marketing, Legal and Staff
| 1.1 Venue Selection after deciding approximate guest limit |  | 2022-03-01 | 2022-03-01 | Marketing
| 1.2 Visiting Shortlisted Venues for deciding final venue |  | 2022-03-02 | 2022-03-02 | Marketing
| 1.3 Signing up for Event |  | 2022-03-03 | 2022-03-03 | Marketing
| 1.4 Contract Signing |  | 2022-03-04 | 2022-03-04 | Marketing
| 1.5 Applying for Permits for Serving Alcohol, Parking, Event |  | 2022-03-05 | 2022-03-05 | Legal and Marketing
| 1.6 Reception of Permits after finalising details and final documentation |  | 2022-03-06 | 2022-03-08 | Legal and Marketing
2. Paid Partners |  | 2 days | 2022-03-08 | 2022-03-09 | Marketing
| 2.1 Arranging sales |  | 2022-03-08 | 2022-03-09 | Marketing
3. Marketing |  | 5 days | 2022-03-10 | 2022-03-14 | Marketing
| 3.1 Designing flyers, creating social media posts |  | 2022-03-10 | 2022-03-10 | Marketing
| 3.2 Mail, email marketing and promotional posts on social media and final attendees |  | 2022-03-11 | 2022-03-13 | Marketing
| 3.3 Send timely reminders |  | 2022-03-13 | 2022-03-14 | Marketing
4.Registration |  | 10 days | 2022-03-15 | 2022-03-24 | Staff
| 4.1 Register people |  | 2022-03-15 | 2022-03-22 | Staff
| 4.2 Send Confirmation |  | 2022-03-23 | 2022-03-24 | Staff
5. DJ |  | 3 days | 2022-03-25 | 2022-03-27 | Marketing
| 5.1 Contacting Various DJ's and teams |  | 2022-03-25 | 2022-03-25 | Marketing
| 5.2 Negotiating demands and total costs |  | 2022-03-25 | 2022-03-26 | Treasury and Marketing
| 5.3 Signing up for Event |  | 2022-03-26 | 2022-03-26 | Treasury and Marketing
| 5.4 Contract Signing |  | 2022-03-26 | 2022-03-27 | Treasury and Marketing
6. Food & Drinks |  | 4 days | 2022-03-28 | 2022-03-31 | Marketing
| 6.1 Contacting Various Major Food Chains & Caterers |  | 2022-03-28 | 2022-03-29 | Marketing
| 6.2 Negotiating demands and total costs |  | 2022-03-29 | 2022-03-30 | Treasury and Marketing
| 6.3 Signing up for Event |  | 2022-03-30 | 2022-03-30 | Treasury and Marketing
| 6.4 Contract Signing |  | 2022-03-31 | 2022-03-31 | Treasury and Marketing
7. Security |  | 3 days | 2022-04-01 | 2022-04-03 | Marketing
| 7.1 Contacting Various Security Firms & Companies |  | 2022-04-01 | 2022-04-01 | Marketing
| 7.2 Negotiating demands and total costs |  | 2022-04-02 | 2022-04-02 | Treasury and Marketing
| 7.3 Signing up for Event |  | 2022-04-02 | 2022-04-02 | Treasury and Marketing
| 7.4 Contract Signing |  | 2022-04-03 | 2022-04-03 | Treasury and Marketing
8. Venue Setup & COVID-19 Measures |  | 5 days | 2022-04-04 | 2022-04-08 | Staff & Security
| 8.1 Decoration, Stage Setup |  | 2022-04-04 | 2022-04-05 | Staff
| 8.2 Lighting and Equipment Setup |  | 2022-04-06 | 2022-04-07 | Staff
| 8.3 COVID-19 Measure check and Sanitizing Stations Setup |  | 2022-04-07 | 2022-04-08 | Staff & Security
EVENT |  | 1 day | 2022-04-10 | 2022-04-10 | Staff & Security

## Hours (2)
| 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | HOURS
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Licencing and Venue | 2022-03-01: 8; 2022-03-02: 8; 2022-03-03: 8; 2022-03-04: 8; 2022-03-05: 8; 2022-03-06: 8; 2022-03-07: 8; 2022-03-08: 8 | 64
Paid Partners | 2022-03-08: 8; 2022-03-09: 8 | 16
Marketing | 2022-03-10: 8; 2022-03-11: 8; 2022-03-12: 8; 2022-03-13: 8; 2022-03-14: 8 | 40
Registration | 2022-03-15: 8; 2022-03-16: 8; 2022-03-17: 8; 2022-03-18: 8; 2022-03-19: 8; 2022-03-20: 8; 2022-03-21: 8; 2022-03-22: 8; 2022-03-23: 8; 2022-03-24: 8 | 80
DJ | 2022-03-25: 8; 2022-03-26: 8; 2022-03-27: 8 | 24
Food and Drinks | 2022-03-28: 8; 2022-03-29: 8; 2022-03-30: 8; 2022-03-31: 8 | 32
Security | 2022-04-01: 8; 2022-04-02: 8; 2022-04-03: 8 | 24
Venue Setup & Covid 19 Measures | 2022-04-04: 8; 2022-04-05: 8; 2022-04-06: 8; 2022-04-07: 8; 2022-04-08: 8 | 40
| 8 | 8 | 8 | 8 | 8 | 8 | 8 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 320
EVENT