## WBS EVENT MANAGEMENT
PROJECT TITLE | Spring Fest |  |  | COMPANY NAME | Party Animal Co.
PROJECT MANAGER | Aashutosh Sehgal, Rohit Rohit | Rakesh Singh,Heta Desai | Devashish Patel | DATE | 02/28/2022
Spring Festival
Registration & Sponsorship
Registration
Paid-Partners
Register People
Arranging corporate sales platform for paid-partners
DJ, Food & Drinks
DJ
Food
Drinks
Meeting various DJ's
Reaching out to major food chains
Reaching out to major alchol suppliers
Licensing & Venue
Licenses
Venue
Applying permit for event, parking, alchol, gathering
Marketing
Designing flyers, social media posts
Mail, email and post flyers on social media
Send timely reminders
Send Confirmation
Negotiating based on demand and cost
Signing them up for event
Signing them up for event
Getting permits
Negotiating based on demand and cost.
Signing them up for event
Negotiating based on demand and cost
Signing them up for event
Selection
Decoration
Visiting various venues appropriate for event
Stage
Lighting
Flowers
Fireworks
Contract signing
Contract signing
Contract signing
Contract signing
Equipments
Meeting Various Security Firms
Negotiating based on demand and cost
Signing up for the Event
Contract Signing