## Resourcce Work Activity
RESOURCE WORK ACTIVITY CHART
Activities |  | Duration | Start | End | Resource
1. Licensing & Venue |  | 8 days | 2022-03-01 | 2022-03-08 | Marketing, Legal and Staff
| 1.1 Venue Selection after deciding approximate guest limit |  | 2022-03-01 | 2022-03-01 | Marketing
| 1.2 Visiting Shortlisted Venues for deciding final venue |  | 2022-03-02 | 2022-03-02 | Marketing
| 1.3 Signing up for Event |  | 2022-03-03 | 2022-03-03 | Marketing
| 1.4 Contract Signing |  | 2022-03-04 | 2022-03-04 | Marketing
| 1.5 Applying for Permits for Serving Alcohol, Parking, Event |  | 2022-03-05 | 2022-03-05 | Legal and Marketing
| 1.6 Reception of Permits after finalising details and final documentation |  | 2022-03-06 | 2022-03-08 | Legal and Marketing
2. Paid Partners |  | 2 days | 2022-03-08 | 2022-03-09 | Marketing
| 2.1 Arranging sales |  | 2022-03-08 | 2022-03-09 | Marketing
3. Marketing |  | 5 days | 2022-03-10 | 2022-03-14 | Marketing
| 3.1 Designing flyers, creating social media posts |  | 2022-03-10 | 2022-03-10 | Marketing
| 3.2 Mail, email marketing and promotional posts on social media and final attendees |  | 2022-03-11 | 2022-03-13 | Marketing
| 3.3 Send timely reminders |  | 2022-03-13 | 2022-03-14 | Marketing
4.Registration |  | 10 days | 2022-03-15 | 2022-03-24 | Staff
| 4.1 Register people |  | 2022-03-15 | 2022-03-22 | Staff
| 4.2 Send Confirmation |  | 2022-03-23 | 2022-03-24 | Staff
5. DJ |  | 3 days | 2022-03-25 | 2022-03-27 | Marketing
| 5.1 Contacting Various DJ's and teams |  | 2022-03-25 | 2022-03-25 | Marketing
| 5.2 Negotiating demands and total costs |  | 2022-03-25 | 2022-03-26 | Treasury and Marketing
| 5.3 Signing up for Event |  | 2022-03-26 | 2022-03-26 | Treasury and Marketing
| 5.4 Contract Signing |  | 2022-03-26 | 2022-03-27 | Treasury and Marketing
6. Food & Drinks |  | 4 days | 2022-03-28 | 2022-03-31 | Marketing
| 6.1 Contacting Various Major Food Chains & Caterers |  | 2022-03-28 | 2022-03-29 | Marketing
| 6.2 Negotiating demands and total costs |  | 2022-03-29 | 2022-03-30 | Treasury and Marketing
| 6.3 Signing up for Event |  | 2022-03-30 | 2022-03-30 | Treasury and Marketing
| 6.4 Contract Signing |  | 2022-03-31 | 2022-03-31 | Treasury and Marketing
7. Security |  | 3 days | 2022-04-01 | 2022-04-03 | Marketing
| 7.1 Contacting Various Security Firms & Companies |  | 2022-04-01 | 2022-04-01 | Marketing
| 7.2 Negotiating demands and total costs |  | 2022-04-02 | 2022-04-02 | Treasury and Marketing
| 7.3 Signing up for Event |  | 2022-04-02 | 2022-04-02 | Treasury and Marketing
| 7.4 Contract Signing |  | 2022-04-03 | 2022-04-03 | Treasury and Marketing
8. Venue Setup & COVID-19 Measures |  | 5 days | 2022-04-04 | 2022-04-08 | Staff & Security
| 8.1 Decoration, Stage Setup |  | 2022-04-04 | 2022-04-05 | Staff
| 8.2 Lighting and Equipment Setup |  | 2022-04-06 | 2022-04-07 | Staff
| 8.3 COVID-19 Measure check and Sanitizing Stations Setup |  | 2022-04-07 | 2022-04-08 | Staff & Security
EVENT |  | 1 day | 2022-04-10 | 2022-04-10 | Staff & Security